## P2S Training
Task id | Week | Description | Duration | Start Date | End Date | Status | 2017-04-09 | [21 empty] | 2017-05-09 | [30 empty] | 2017-06-09 | [29 empty] | 2017-07-10 | [30 empty] | 2017-08-10 | [30 empty] | 2017-09-10 | [29 empty] | 2017-10-11 | [30 empty] | 2017-11-11 | [29 empty] | 2017-12-12 | [30 empty] | 2018-01-12 | [30 empty] | 2018-02-12
 | time axis 2017-04-09 to 2018-02-28
Phase 1 - Building an Online Presence
1 | WK 1 | Laying the Foundations |  | 2017-04-09 | 2017-04-14 | bar: 2017-04-09 to 2017-04-14
1.1 | WK 1 | Find domain | 0.25 | 2017-04-09 | 2017-04-09 06:00 | bar: 2017-04-09
1.2 | WK 1 | Register / Hosting | 0.25 | 2017-04-09 06:00 | 2017-04-09 12:00 | bar: 2017-04-09
1.3 | WK 1 | Log in to control panel | 0.5 | 2017-04-09 12:00 | 2017-04-10 | bar: 2017-04-09 to 2017-04-10
1.4 | WK 1 | install Wordpress Blog System | 0.5 | 2017-04-10 | 2017-04-10 12:00 | bar: 2017-04-10
1.5 | WK 1 | prep Blog for Editing | 0.5 | 2017-04-10 12:00 | 2017-04-11 | bar: 2017-04-10 to 2017-04-11
1.6 | WK 1 | Update Blog Settings | 0.5 | 2017-04-11 | 2017-04-11 12:00 | bar: 2017-04-11
1.7 | WK 1 | Write 1st blog post | 0.5 | 2017-04-11 12:00 | 2017-04-12 | bar: 2017-04-11 to 2017-04-12
1.8 | WK 1 | Set up email account | 0.5 | 2017-04-12 | 2017-04-12 12:00 | bar: 2017-04-12
1.9 | WK 1 | write more blog posts | 0.5 | 2017-04-12 12:00 | 2017-04-13 | bar: 2017-04-12 to 2017-04-13
1.10 | WK 1 | Read 'The Go Giver' | 1 | 2017-04-13 | 2017-04-14 | bar: 2017-04-13 to 2017-04-14
2 | WK 2 | Improving Blog Appearance |  | 2017-04-16 | 2017-04-20 | bar: 2017-04-16 to 2017-04-20
2.1 | WK 2 | Order OptimisePress | 0.25 | 2017-04-16 | 2017-04-16 06:00 | bar: 2017-04-16
2.2 | WK 2 | Create a P2S folder | 0.25 | 2017-04-16 06:00 | 2017-04-16 12:00 | bar: 2017-04-16
2.3 | WK 2 | Download OptimisePress theme | 0.25 | 2017-04-16 12:00 | 2017-04-16 18:00 | bar: 2017-04-16
2.4 | WK 2 | Upload OptimisePress theme | 0.25 | 2017-04-16 18:00 | 2017-04-17 | bar: 2017-04-16 to 2017-04-17
2.5 | WK 2 | Activate and license OptimisePress | 0.25 | 2017-04-17 | 2017-04-17 06:00 | bar: 2017-04-17
2.6 | WK 2 | Set Basic blog settings | 0.5 | 2017-04-17 06:00 | 2017-04-17 18:00 | bar: 2017-04-17
2.7 | WK 2 | Prep blog for plugins | 0.25 | 2017-04-17 18:00 | 2017-04-18 | bar: 2017-04-17 to 2017-04-18
2.8 | WK 2 | Install plugins | 0.25 | 2017-04-18 | 2017-04-18 06:00 | bar: 2017-04-18
2.9 | WK 2 | Add About Me page | 0.5 | 2017-04-18 06:00 | 2017-04-18 18:00 | bar: 2017-04-18
2.10 | WK 2 | Add pages to menu | 0.25 | 2017-04-18 18:00 | 2017-04-19 | bar: 2017-04-18 to 2017-04-19
2.11 | WK 2 | Read Bloggers Roadmap | 1 | 2017-04-19 | 2017-04-20 | bar: 2017-04-19 to 2017-04-20
3 | WK 3 | List Building Part 1 |  | 2017-04-23 | 2017-04-25 12:00 | bar: 2017-04-23 to 2017-04-25
3.1 | WK 3 | Register for Aweber | 0.25 | 2017-04-23 | 2017-04-23 06:00 | bar: 2017-04-23
3.2 | WK 3 | Create 1st Mailing list | 0.25 | 2017-04-23 06:00 | 2017-04-23 12:00 | bar: 2017-04-23
3.3 | WK 3 | Edit Confirmation Message | 0.25 | 2017-04-23 12:00 | 2017-04-23 18:00 | bar: 2017-04-23
3.4 | WK 3 | Add follow up email | 0.5 | 2017-04-23 18:00 | 2017-04-24 06:00 | bar: 2017-04-23 to 2017-04-24
3.5 | WK 3 | Create Sign Up Form | 0.5 | 2017-04-24 06:00 | 2017-04-24 18:00 | bar: 2017-04-24
3.6 | WK 3 | Connect OptimisePress to Aweber | 0.25 | 2017-04-24 18:00 | 2017-04-25 | bar: 2017-04-24 to 2017-04-25
3.7 | WK 3 | Add Opt In form to blog | 0.5 | 2017-04-25 | 2017-04-25 12:00 | bar: 2017-04-25
4 | WK 4 | Adding Social Media Profiles |  | 2017-04-30 | 2017-04-30 12:00 | bar: 2017-04-30
4.1 | WK 4 | Set Up Social Media Accounts | 1 | 2017-04-30 | 2017-05-01 | bar: 2017-04-30 to 2017-05-01
4.2 | WK 4 | Download and install Social Media Icons | 0.25 | 2017-05-01 | 2017-05-01 06:00 | bar: 2017-05-01
4.3 | WK 4 | Add top sidebar code | 0.5 | 2017-05-01 06:00 | 2017-05-01 18:00 | bar: 2017-05-01
4.4 | WK 4 | Add code to blog | 0.25 | 2017-05-01 18:00 | 2017-05-02 | bar: 2017-05-01 to 2017-05-02
4.5 | WK 4 | Complete 'Wrap up tasks" (Video 5) | 0.5 | 2017-04-30 | 2017-04-30 12:00 | bar: 2017-04-30
5 | WK 5 | Blog Networking |  | 2017-05-07 | 2017-05-01
5.1 | WK 5 | Add any social media buttons | 0.25 | 2017-05-07 | 2017-05-07 06:00 | bar: 2017-05-07
5.2 | WK 5 | Edit size of sidebar | 0.25 | 2017-05-07 06:00 | 2017-05-07 12:00 | bar: 2017-05-07
5.3 | WK 5 | Download & install 'Widlink' plugin | 0.25 | 2017-05-07 12:00 | 2017-05-07 18:00 | bar: 2017-05-07
5.4 | WK 5 | Set Up Widlink widget | 0.25 | 2017-05-07 18:00 | 2017-05-08 | bar: 2017-05-07 to 2017-05-08
5.5 | WK 5 | Add Blog to Partnership network | 0.25 | 2017-05-08 | 2017-05-08 06:00 | bar: 2017-05-08
5.6 | WK 5 | Apply for Google Adsense | 1 | 2017-05-08 06:00 | 2017-05-09 06:00 | bar: 2017-05-08 to 2017-05-09
6 | WK 6 | Monetising your blog |  | 2017-05-14
6.1 | WK 6 | Read the Adsense guide and understand how it works | 1 | 2017-05-14 | 2017-05-15 | bar: 2017-05-14 to 2017-05-15
6.2 | WK 6 | Install the GARD plugin | 0.25 | 2017-05-15 | 2017-05-15 06:00 | bar: 2017-05-15
6.3 | WK 6 | Connect the GARD plugin to Adsense | 0.25 | 2017-05-15 06:00 | 2017-05-15 12:00 | bar: 2017-05-15
6.4 | WK 6 | Add some Ads to your blog | 1 | 2017-05-15 12:00 | 2017-05-16 12:00 | bar: 2017-05-15 to 2017-05-16
6.5 | WK 6 | Register with Clickbank | 0.25 | 2017-05-16 12:00 | 2017-05-16 18:00 | bar: 2017-05-16
6.6 | WK 6 | Apply to be whitelisted for simple traffic solutions | 0.25 | 2017-05-16 18:00 | 2017-05-17 | bar: 2017-05-16 to 2017-05-17
6.7 | WK 6 | Add banners | 1 | 2017-05-17 | 2017-05-18 | bar: 2017-05-17 to 2017-05-18
7 | WK 7 | Essential Blogging Techniques |  | 2017-05-21
7.1 | WK 7 | Upload and Activate Insta Legal Pages plugin | 0.25 | 2017-05-21 | 2017-05-21 06:00 | bar: 2017-05-21
7.2 | WK 7 | Use Insta legal pages to create necessary legal pages | 1 | 2017-05-21 06:00 | 2017-05-22 06:00 | bar: 2017-05-21 to 2017-05-22
7.3 | WK 7 | Add images to future blog posts | 0.25 | 2017-05-22 06:00 | 2017-05-22 12:00 | bar: 2017-05-22
7.4 | WK 7 | Add videos to blog posts | 0.5 | 2017-05-22 12:00 | 2017-05-23 | bar: 2017-05-22 to 2017-05-23
7.5 | WK 7 | Prep blog posts in advance and schedule | 1 | 2017-05-23 | 2017-05-24 | bar: 2017-05-23 to 2017-05-24
7.6 | WK 7 | Send email at same time to blog subscribers | 0.5 | 2017-05-24 | 2017-05-24 12:00 | bar: 2017-05-24
7.7 | WK 7 | Check out bloggers roadmap | 1.5 | 2017-05-24 12:00 | 2017-05-26 | bar: 2017-05-24 to 2017-05-26
8 | WK 8 | ListBuilding Part 2 |  | 2017-05-28
8.1 | WK 8 | Submit Clickbank id to be whitelisted | 0.25 | 2017-05-28 | 2017-05-28 06:00 | bar: 2017-05-28
8.2 | WK 8 | Install and set up link supercharger | 0.5 | 2017-05-28 06:00 | 2017-05-28 18:00 | bar: 2017-05-28
8.3 | WK 8 | download files and choose which to use | 0.5 | 2017-05-28 18:00 | 2017-05-29 06:00 | bar: 2017-05-28 to 2017-05-29
8.4 | WK 8 | Set Up new Aweber list | 0.25 | 2017-05-29 06:00 | 2017-05-29 12:00 | bar: 2017-05-29
8.5 | WK 8 | Edit Aweber email confirmation | 0.25 | 2017-05-29 12:00 | 2017-05-29 18:00 | bar: 2017-05-29
8.6 | WK 8 | Set up Aweber pop up settings | 0.25 | 2017-05-29 18:00 | 2017-05-30 | bar: 2017-05-29 to 2017-05-30
8.7 | WK 8 | Add Aweber pop up to blog | 1 | 2017-05-30 | 2017-05-31 | bar: 2017-05-30 to 2017-05-31
8.8 | WK 8 | Add follow up messagesto Autoresponder | 1 | 2017-05-31 | 2017-06-01 | bar: 2017-05-31 to 2017-06-01
8.9 | WK 8 | Test | 1 | 2017-06-01 | 2017-06-02 | bar: 2017-06-01 to 2017-06-02
Phase 2 - Product Creation Step 1
9 | WK 9 | Niche Selection Part 1 | 7 | 2017-06-04 | 2017-06-11 | bar: 2017-06-04 to 2017-06-11
9.1 | WK 9
9.2 | WK 9
9.3 | WK 9
9.4 | WK 9
9.5 | WK 9
9.6 | WK 9
9.7 | WK 9
9.8 | WK 9
9.9 | WK 9
10 | WK 10 | Niche Selection Part 2 | 7 | 2017-06-11 | 2017-06-18 | bar: 2017-06-11 to 2017-06-18
10.1 | WK 10
10.2 | WK 10
10.3 | WK 10
10.4 | WK 10
10.5 | WK 10
10.6 | WK 10
10.7 | WK 10
10.8 | WK 10
10.9 | WK 10
11 | WK 11 | Essential Research | 7 | 2017-06-18 | 2017-06-25 | bar: 2017-06-18 to 2017-06-25
11.1 | WK 11
11.2 | WK 11
11.3 | WK 11
11.4 | WK 11
11.5 | WK 11
11.6 | WK 11
11.7 | WK 11
11.8 | WK 11
11.9 | WK 11
12 | WK 12 | Mind Mapping Your Product | 7 | 2017-06-25 | 2017-07-02 | bar: 2017-06-25 to 2017-07-02
12.1 | WK 12
12.2 | WK 12
12.3 | WK 12
12.4 | WK 12
12.5 | WK 12
12.6 | WK 12
12.7 | WK 12
12.8 | WK 12
12.9 | WK 12
13 | WK 13 | Naming Your Product | 7 | 2017-07-02 | 2017-07-09 | bar: 2017-07-02 to 2017-07-09
13.1 | WK 13
13.2 | WK 13
13.3 | WK 13
13.4 | WK 13
13.5 | WK 13
13.6 | WK 13
13.7 | WK 13
13.8 | WK 13
13.9 | WK 13
14 | WK 14 | Product Creation Software | 7 | 2017-07-09 | 2017-07-16 | bar: 2017-07-09 to 2017-07-16
14.1 | WK 14
14.2 | WK 14
14.3 | WK 14
14.4 | WK 14
14.5 | WK 14
14.6 | WK 14
14.7 | WK 14
14.8 | WK 14
14.9 | WK 14
15 | WK 15 | Begin Product Creatoion | 7 | 2017-07-16 | 2017-07-23 | bar: 2017-07-16 to 2017-07-23
15.1 | WK 15
15.2 | WK 15
15.3 | WK 15
15.4 | WK 15
15.5 | WK 15
15.6 | WK 15
15.7 | WK 15
15.8 | WK 15
15.9 | WK 15
16 | WK 16 | Creating Video Part 1 | 7 | 2017-07-23 | 2017-07-30 | bar: 2017-07-23 to 2017-07-30
16.1 | WK 16
16.2 | WK 16
16.3 | WK 16
16.4 | WK 16
16.5 | WK 16
16.6 | WK 16
16.7 | WK 16
16.8 | WK 16
16.9 | WK 16
17 | WK 17 | Creating Video continued | 7 | 2017-07-30 | 2017-08-06 | bar: 2017-07-30 to 2017-08-06
17.1 | WK 17
17.2 | WK 17
17.3 | WK 17
17.4 | WK 17
17.5 | WK 17
17.6 | WK 17
17.7 | WK 17
17.8 | WK 17
17.9 | WK 17
18 | WK 18 | Creating Audio | 7 | 2017-08-06 | 2017-08-13 | bar: 2017-08-06 to 2017-08-13
18.1 | WK 18
18.2 | WK 18
18.3 | WK 18
18.4 | WK 18
18.5 | WK 18
18.6 | WK 18
18.7 | WK 18
18.8 | WK 18
18.9 | WK 18
19 | WK 19 | Main Product Completion | 7 | 2017-08-13 | 2017-08-20 | bar: 2017-08-13 to 2017-08-20
19.1 | WK 19
19.2 | WK 19
19.3 | WK 19
19.4 | WK 19
19.5 | WK 19
19.6 | WK 19
19.7 | WK 19
19.8 | WK 19
19.9 | WK 19
20 | WK 20 | Upsells and Sales Funnels | 7 | 2017-08-20 | 2017-08-27 | bar: 2017-08-20 to 2017-08-27
20.1 | WK 20
20.2 | WK 20
20.3 | WK 20
20.4 | WK 20
20.5 | WK 20
20.6 | WK 20
20.7 | WK 20
20.8 | WK 20
20.9 | WK 20
21 | WK 21 | Connecting with John | 7 | 2017-08-27 | 2017-09-03 | bar: 2017-08-27 to 2017-09-03
21.1 | WK 21
21.2 | WK 21
21.3 | WK 21
21.4 | WK 21
21.5 | WK 21
21.6 | WK 21
21.7 | WK 21
21.8 | WK 21
21.9 | WK 21
Phase 3 - Your Member's Area
22 | WK 22 | Members Area Basics | 7 | 2017-09-03 | 2017-09-10 | bar: 2017-09-03 to 2017-09-10
22.1 | WK 22
22.2 | WK 22
22.3 | WK 22
22.4 | WK 22
22.5 | WK 22
22.6 | WK 22
22.7 | WK 22
22.8 | WK 22
22.9 | WK 22
23 | WK 23 | Adding Video to your members area | 7 | 2017-09-10 | 2017-09-17 | bar: 2017-09-10 to 2017-09-17
23.1 | WK 23
23.2 | WK 23
23.3 | WK 23
23.4 | WK 23
23.5 | WK 23
23.6 | WK 23
23.7 | WK 23
23.8 | WK 23
23.9 | WK 23
24 | WK 24 | Adding other content to your members area | 7 | 2017-09-17 | 2017-09-24 | bar: 2017-09-17 to 2017-09-24
24.1 | WK 24
24.2 | WK 24
24.3 | WK 24
24.4 | WK 24
24.5 | WK 24
24.6 | WK 24
24.7 | WK 24
24.8 | WK 24
24.9 | WK 24
25 | WK 25 | Your welcome page | 7 | 2017-09-24 | 2017-10-01 | bar: 2017-09-24 to 2017-10-01
25.1 | WK 25
25.2 | WK 25
25.3 | WK 25
25.4 | WK 25
25.5 | WK 25
25.6 | WK 25
25.7 | WK 25
25.8 | WK 25
25.9 | WK 25
26 | WK 26 | Setting Up a Support Desk | 7 | 2017-10-01 | 2017-10-08 | bar: 2017-10-01 to 2017-10-08
26.1 | WK 26
26.2 | WK 26
26.3 | WK 26
26.4 | WK 26
26.5 | WK 26
26.6 | WK 26
26.7 | WK 26
26.8 | WK 26
26.9 | WK 26
Phase 4 - Sales Page Creation
27 | WK 27 | Sales Letter ABC | 7 | 2017-10-08 | 2017-10-15 | bar: 2017-10-08 to 2017-10-15
27.1 | WK 27
27.2 | WK 27
27.3 | WK 27
27.4 | WK 27
27.5 | WK 27
27.6 | WK 27
27.7 | WK 27
27.8 | WK 27
27.9 | WK 27
28 | WK 28 | Seven Steps to Selling | 7 | 2017-10-15 | 2017-10-22 | bar: 2017-10-15 to 2017-10-22
28.1 | WK 28
28.2 | WK 28
28.3 | WK 28
28.4 | WK 28
28.5 | WK 28
28.6 | WK 28
28.7 | WK 28
28.8 | WK 28
28.9 | WK 28
29 | WK 29 | Sales Page SetUp | 7 | 2017-10-22 | 2017-10-29 | bar: 2017-10-22 to 2017-10-29
29.1 | WK 29
29.2 | WK 29
29.3 | WK 29
29.4 | WK 29
29.5 | WK 29
29.6 | WK 29
29.7 | WK 29
29.8 | WK 29
29.9 | WK 29
30 | WK 30 | Writing Your Sales Page part 1 | 7 | 2017-10-29 | 2017-11-05 | bar: 2017-10-29 to 2017-11-05
30.1 | WK 30
30.2 | WK 30
30.3 | WK 30
30.4 | WK 30
30.5 | WK 30
30.6 | WK 30
30.7 | WK 30
30.8 | WK 30
30.9 | WK 30
31 | WK 31 | Writing Your Sales Page part 2 | 7 | 2017-11-05 | 2017-11-12 | bar: 2017-11-05 to 2017-11-12
31.1 | WK 31
31.2 | WK 31
31.3 | WK 31
31.4 | WK 31
31.5 | WK 31
31.6 | WK 31
31.7 | WK 31
31.8 | WK 31
31.9 | WK 31
32 | WK 32 | Writing Your Sales Page part 3 | 7 | 2017-11-12 | 2017-11-19 | bar: 2017-11-12 to 2017-11-19
32.1 | WK 32
32.2 | WK 32
32.3 | WK 32
32.4 | WK 32
32.5 | WK 32
32.6 | WK 32
32.7 | WK 32
32.8 | WK 32
32.9 | WK 32
33 | WK 33 | Writing Your Sales Page part 4 | 7 | 2017-11-19 | 2017-11-26 | bar: 2017-11-19 to 2017-11-26
33.1 | WK 33
33.2 | WK 33
33.3 | WK 33
33.4 | WK 33
33.5 | WK 33
33.6 | WK 33
33.7 | WK 33
33.8 | WK 33
33.9 | WK 33
Phase 5 - The rest of your site
34 | WK 34 | protecting your content | 7 | 2017-11-26 | 2017-12-03 | bar: 2017-11-26 to 2017-12-03
34.1 | WK 34
34.2 | WK 34
34.3 | WK 34
34.4 | WK 34
34.5 | WK 34
34.6 | WK 34
34.7 | WK 34
34.8 | WK 34
34.9 | WK 34
35 | WK 35 | Adding Products to JV Zoo | 7 | 2017-12-03 | 2017-12-10 | bar: 2017-12-03 to 2017-12-10
35.1 | WK 35
35.2 | WK 35
35.3 | WK 35
35.4 | WK 35
35.5 | WK 35
35.6 | WK 35
35.7 | WK 35
35.8 | WK 35
35.9 | WK 35
36 | WK 36 | Creating your JV page | 7 | 2017-12-10 | 2017-12-17 | bar: 2017-12-10 to 2017-12-17
36.1 | WK 36
36.2 | WK 36
36.3 | WK 36
36.4 | WK 36
36.5 | WK 36
36.6 | WK 36
36.7 | WK 36
36.8 | WK 36
36.9 | WK 36
37 | WK 37 | Completing your JV page | 7 | 2017-12-17 | 2017-12-24 | bar: 2017-12-17 to 2017-12-24
37.1 | WK 37
37.2 | WK 37
37.3 | WK 37
37.4 | WK 37
37.5 | WK 37
37.6 | WK 37
37.7 | WK 37
37.8 | WK 37
37.9 | WK 37
38 | WK 38 | Reviewing your product | 7 | 2017-12-24 | 2017-12-31 | bar: 2017-12-24 to 2017-12-31
38.1 | WK 38
38.2 | WK 38
38.3 | WK 38
38.4 | WK 38
38.5 | WK 38
38.6 | WK 38
38.7 | WK 38
38.8 | WK 38
38.9 | WK 38
39 | WK 39 | Launching your product | 7 | 2017-12-31 | 2018-01-07 | bar: 2017-12-31 to 2018-01-07
39.1 | WK 39
39.2 | WK 39
39.3 | WK 39
39.4 | WK 39
39.5 | WK 39
39.6 | WK 39
39.7 | WK 39
39.8 | WK 39
39.9 | WK 39
Phase 6 - Post Launch Products
40 | WK 40 | The Evergreen model | 7 | 2018-01-07 | 2018-01-14 | bar: 2018-01-07 to 2018-01-14
40.1 | WK 40
40.2 | WK 40
40.3 | WK 40
40.4 | WK 40
40.5 | WK 40
40.6 | WK 40
40.7 | WK 40
40.8 | WK 40
40.9 | WK 40
41 | WK 41 | Evergreen promotions part 1 | 7 | 2018-01-14 | 2018-01-21 | bar: 2018-01-14 to 2018-01-21
41.1 | WK 41
41.2 | WK 41
41.3 | WK 41
41.4 | WK 41
41.5 | WK 41
41.6 | WK 41
41.7 | WK 41
41.8 | WK 41
41.9 | WK 41
42 | WK 42 | Evergreen promotions part 2 | 7 | 2018-01-21 | 2018-01-28 | bar: 2018-01-21 to 2018-01-28
42.1 | WK 42
42.2 | WK 42
42.3 | WK 42
42.4 | WK 42
42.5 | WK 42
42.6 | WK 42
42.7 | WK 42
42.8 | WK 42
42.9 | WK 42
43 | WK 43 | Evergreen promotions part 3 | 7 | 2018-01-28 | 2018-02-04 | bar: 2018-01-28 to 2018-02-04
43.1 | WK 43
43.2 | WK 43
43.3 | WK 43
43.4 | WK 43
43.5 | WK 43
43.6 | WK 43
43.7 | WK 43
43.8 | WK 43
43.9 | WK 43
Phase 7 - Advanced Techniques
44 | WK 44 | Email marketing tactics | 7 | 2018-02-04 | 2018-02-11 | bar: 2018-02-04 to 2018-02-11
44.1 | WK 44
44.2 | WK 44
44.3 | WK 44
44.4 | WK 44
44.5 | WK 44
44.6 | WK 44
44.7 | WK 44
44.8 | WK 44
44.9 | WK 44
45 | WK 45 | SuperAffiliate Tactics | 7 | 2018-02-11 | 2018-02-18 | bar: 2018-02-11 to 2018-02-18
45.1 | WK 45
45.2 | WK 45
45.3 | WK 45
45.4 | WK 45
45.5 | WK 45
45.6 | WK 45
45.7 | WK 45
45.8 | WK 45
45.9 | WK 45

## Regular Tasks
Ref | Description | Frequency (every x days) | last completed | Next Due | Status
PLANNING
1 | To Do List | 1 | 2017-04-30 | 2017-05-01
2 | DailyPlan update | 1 | 2017-04-30 | 2017-05-01
3 | Weekly Plan update | 7 | 2017-04-29 | 2017-05-06
BLOGGING
1 | Write new blog post and post to social media | 2 | 2017-04-28 | 2017-04-30 | TODAY
2 | Comment on other p2s blogs | 2 | 2017-04-30 | 2017-05-02
3 | comment on other blogs | 2 | 2017-04-30 | 2017-05-02
0
0
0
Formulas:
Next Due = [last completed]+[Frequency (every x days)]
Status = IF([Next Due]=TODAY(),"TODAY",IF(AND([Next Due]<TODAY(),[Next Due]>0),"OVERDUE",""))