## Summary
Property Development Feasibility Assessment		BUY, DEVELOP, SELL

Instructions	Fill in the cells shaded GREEN
	DO NOT change the cells ahaded grey
	When you add a confidence level.	If you choose 'High Confidence' the calculation will assume best case cost is most likely
		If you choose 'Medium' or leave blank, the calculation will assume most likely is half way between best and worst case costs
		If you choose 'Low' the calculation will assume worst case cost is most likely

	Description	Best Case	Worst Case	Most Likely	Confidence Level
Ceiling Price	Maximum Price you expect to be able to achieve when you sell	250,000	220,000	235,000	Medium
Work Required		Best Case	Worst Case	Most Likely
Building		14,000	27,000	25,500
Refurb		15,250	25,000	17,875
Garden & Grounds		5,000	7,000	6,000
Total Costs of work		34,250	59,000	49,375
Contingency	10%	1,400	2,700	2,550
Total Cost of Work		35,650	61,700	51,925
Project Duration (Weeks)		20	32	26	Medium
Time to Sell After Completion		6	12	9	Medium
Buying & Selling Costs		Best Case	Worst Case	Most Likely
Legal Costs	Buyer	1,000	1,500	1,250	Medium
	Seller	1,000	1,500	1,250	Medium
Agent Fees	Assume 1% of selling price	2,500	2,200	2,350
Taxes	Assume 1.5% of selling price	3,750	3,300	3,525	Medium
Total Buying & Selling Costs		8,250	8,500	8,375
Finance	Amount	Best Case	Worst Case	Most Likely
Mortgage (Interest Only)	100000	1,625	4,583	3,104
Borrowing for Costs of Work	20000	2,765	5,143	3,954
Total Cost of Finance		4,390	9,726	7,058
Desired Profit		Best Case	Worst Case	Most Likely
Minimum Profit per week		1,500	1,000	1,000	Low
Required Profit		30,000	32,000	31,000
Maximum Purchase Price		High Risk	Low Risk	Mid Risk
	To cover costs of works, finance and make required profit	171,710	108,074	136,642

## Building_Costs
Instructions	List ALL work required with estimated best and worst case costs
	Add a confidence level.	If you choose 'High Confidence' the calculation will assume best case cost is most likely
		If you choose 'Medium' or leave blank, the calculation will assume most likely is half way between best and worst case costs
		If you choose 'Low' the calculation will assume worst case cost is most likely

Work Required		Best Case Cost	Worst Case Cost		Confidence Level
Structural	repair roof	10,000	20,000	20,000	Low
Exterior	make good / paint	1,500	3,000	2,250	Medium
Doors and windows	replace throughout	2,500	4,000	3,250	Medium

## Refurb_costs
Instructions	List ALL work required with estimated best and worst case costs
	Add a confidence level.	If you choose 'High Confidence' the calculation will assume best case cost is most likely
		If you choose 'Medium' or leave blank, the calculation will assume most likely is half way between best and worst case costs
		If you choose 'Low' the calculation will assume worst case cost is most likely

Work Required		Best Case Cost	Worst Case Cost		Confidence Level
kitchen	replace	4,000	7,000	4,000	High
bathroom(s)	replace	3,000	5,000	3,000	High
layout	remove wall between kitchen and dining room	2,000	4,000	3,000	Medium
plumbing	Materials only	250	500	375	Medium
electrical	Outsource	1,000	1,500	1,250	Medium
plastering	Outsource	2,000	2,500	2,250	Medium
decorating	Materials only - tiles, paint	1,500	2,500	2,000	Medium
fixtures and fittings		1,500	2,000	2,000	Low

## Garden_&_Grounds
Instructions	List ALL work required with estimated best and worst case costs
	Add a confidence level.	If you choose 'High Confidence' the calculation will assume best case cost is most likely
		If you choose 'Medium' or leave blank, the calculation will assume most likely is half way between best and worst case costs
		If you choose 'Low' the calculation will assume worst case cost is most likely

Work Required		Best Case Cost	Worst Case Cost		Confidence Level
Landscape		5,000	7,000	6,000	Medium

## Finance
Instructions	Fill in the cells shaded GREEN
	DO NOT change the cells ahaded grey
	When you add a confidence level:	If you choose 'High Confidence' the calculation will assume best case cost is most likely
		If you choose 'Medium' or leave blank, the calculation will assume most likely is half way between best and worst case costs
		If you choose 'Low' the calculation will assume worst case cost is most likely

Mortgage		Best case	Worst Case		Confidence Level
Mortgage Amount	100,000
Annualised Interest Rate (Estimated)		3.00%	5.00%	4.00%	Medium
Monthly Mortgage Repayment (Estimated)	Simple Interest Only	250	417	333
Time to sell (after completion) - weeks		6	12	9	Medium
Total Mortgage Cost		1,625	4,583	3,104	Medium

Other Borrowing		Best case	Worst Case		Confidence Level
Borrowing for Costs of Work	20000
Annualised Interest Rate (Estimated)		5.00%	7.00%	6.00%	Medium
Term (Years)	5
Monthly repayment (Estimated)		425	468	446	Medium
Total Cost	Clear loan as soon as possible	2,765	5,143	3,954	Medium